## Slide 1: Lean Six Sigma Project – Improve On-Time Deliveries
Submitted by - The Best Group (Jayesh, Richmond and Haito)

## Slide 2: Problem Statement
Executive Summary - ABC Manufacturing Co. is a maker of consumer durables that has initiated a project to improve the on-time deliveries from its warehouse to the factory from a current level of 87.9% to 98%. On-time delivery at the factory is a critical metric to measure warehouse performance.
Business Problem - ABC Manufacturing Co. runs a factory that relies on timely deliveries of various components from its warehouse. Maintaining high on-time delivery (OTD) rates is vital for continuous mass production and ensuring sales to end customers, as well as for facilitating future expansion. However, an examination of the past year's delivery performance reveals an OTD rate of 87.9%, which has led to production and sales setbacks at the factory. Consequently, this project aims to enhance the OTD rate to meet the factory's requirements.
Statistical Problem - The present on-time delivery percentage stands at 87.9%, as per the data from the previous year. The objective is to elevate it to 98%.

## Slide 3: Proposed Solution
Statistical Analysis: The underlying reasons for the low on-time delivery percentage include significant fluctuations in factory demand, variability in deliveries from suppliers to the warehouse, inefficiencies and inaccuracies in warehouse stock management due to manual procedures, absence of standardized practices, driver shortages, and extended lead times.
To address these issues, several improvement measures have been implemented, including enhancing Sales and Operations Planning (S&OP) maturity at ABC Manufacturing through collaborative planning and forecasting, enhancing efficiency and accuracy in stock management via process automation (WMS) and training, standardizing processes, optimizing driver recruitment and retention strategies, and reducing lead times through standardized procedures and training.
.

## Slide 4: SIPOC
S | I | P | O | C
SUPPLIERS | INPUTS | PROCESSES | OUTPUTS | CUSTOMERS
Factory | Forecast of demand | Production/logistics capacity planning at Suppliers, Warehouse | Adequate capacity to meet demand & on-time deliveries | Suppliers, W/H
Suppliers of components | On-time supply of components | Maintain inventory at specified levels at W/H | Adequate inventory to meet service levels | W/H
Factory | Delivery Schedule | Sort/pack & dispatch required components from W/H | Payload deliveries | Factory
Driver coordinator at W/H | Suitable truck, driver | Provide truck & driver to shipping dock | Empty truck ready for loading | Shipping personnel at W/H
Shipping personnel at W/H | Components, Invoice, Excise/Sales Tax documents, Gate pass | Load payload on the truck, provide documents | Full truck ready for dispatch to factory | Drivers at W/H
Drivers | Delivery Schedule, payload, documents | Arrive with payload at factory unloading dock | Unloading at factory dock | Factory receiving personnel
Factory receiving personnel | Payload, documents | Unloading at factory dock, confirmation of receipt | Receipt confirmation, delivery update by drivers | Driver, driver coordinator at W/H

## Slide 5: Identify Stakeholders and VOC
Stakeholder | Who | Voice
Customer | Factory | Eliminate Production/Sales losses due to Late Deliveries
Shipping personnel | Warehouse | Want accurate delivery schedule, on-time receipt of empty trucks/drivers to improve on-time deliveries
Driver coordinators | Warehouse | Want accurate delivery schedule, on-time dispatch information, correct location of trucks to improve on-time deliveries
Drivers | Warehouse | Want accurate delivery schedule, correct location of trucks, on-time dispatch from W/H to improve on-time deliveries
Suppliers of components | Suppliers | Want accurate forecast and stock-levels at warehouse to improve on-time deliveries
VOC : Improve on-time deliveries

## Slide 6: CTQ Drill-down
Eliminate Production/Sales losses due to
Late Deliveries
Customer
Need
CTQ
Output Characteristic
On-time Deliveries
On-time Deliveries%
≥ 98%
100%
Late delivery,
1 opportunity for error
Target
Specification/
Tolerance limits
Specification/
Tolerance limits
Defect Definition
Notes: Critical-to-quality, or CTQ, is a six sigma term used to describe aspects of a business that are necessary to ensure customer needs are met. Six sigma is a system used to increase efficiency in a business.

## Slide 7: Project Charter
Project Title – Improve On-Time Delivery %
Process Information –
Business – ABC Manufacturing Co.
Support Function – Warehouse
Team –
Project Champion – Jayesh
Process Owner – ABC Project Leader – Richmond, Haito
Key Milestone Review
Define - 7th Jan 2024
Measure – 15th Jan 2024
Analyze – 25th Jan 2024
Improve – 24th Jun 2024
Validate – 5th Oct 2024
Control – 20th Oct 2024
Project Delight Parameters – Project ‘Y’
On-Time Delivery Efficiency Improvement
Business Case – The current OTD performance of the warehouse is an average of 87.9% based on the past 1 year of data, which is below the target of 100%, leading to customer dissatisfaction due to production & sales losses.
Problem Statement – Average OTD for the past 1 year is at 87.9% not meeting the customer target at 100%.
Goal Statement – To increase On-Time delivery (OTD) from 87.9 to 98%
Project Scope – All deliveries from the warehouse to ABC Manufacturing Factory
Project Plan – Start 7th Jan 2024, End 20th Oct 2024
Resources – Warehouse Database

## Slide 8: High Level Process Map
Warehouse
(Supply & Inventory management)
Bi-weekly Schedule
Daily/weekly Deliveries
Supplier 1
Supplier 2
Supplier N
ABC Manufacturing Factory
Monthly forecast
Daily /weekly
Deliveries
(VMI)

## Slide 9: Detailed Process Map
Truck available?
Yes
Share schedule with shipping personnel
Responsibility: W/H Incharge
Receive Delivery schedule from factory
▪Locate required components at W/H
▪Pack scheduled quantity
▪Prepare Invoice, Tax documents
▪Inform driver coordinator about dispatch
Responsibility: Shipping Personnel
Wait
No
Check actual availability of the truck at the depot
Responsibility: Driver
Take the truck to the loading dock
Responsibility: Driver
Request Driver coordinator to locate alternate truck
Responsibility: Driver
▪ Take the truck to the Un-loading dock at customer factory
▪ Inform receiving personnel 30min before arrival
Responsibility: Driver
▪Unload the payload
▪Check Invoice, Tax documents
▪Give receipt confirmation to driver
Responsibility: Customer receiving Personnel
Check Backhaul payload with Driver coordinator
Responsibility: Driver/coordinator
Backhaul?
Yes
No
Take the empty truck back to W/H depot
Responsibility: Driver
▪Load the payload onto the truck
▪Handover Invoice, Tax documents, Gate pass to driver
Responsibility: Shipping Personnel
▪Locate suitable truck at the depot
▪Assign an available driver for the dispatch
▪Inform driver about dispatch details
▪Record truck request-time, dispatch-time, driver name, loading dock & destination details in W/H Database
Responsibility: Driver coordinator

## Slide 10: Data collection plan
Measure/ Metric | X or Y | Data type | Operational Definition | How to measure | Data Source
Total deliveries | X | Discrete | Number of Total deliveries per day |  | Daily delivery report
On-time deliveries | X | Discrete | Number of On-time deliveries per day |  | Daily delivery report
OTD% | Y | Continuous | Calculated % of on-time deliveries per day by total deliveries per day | (Number of on-time deliveries per day / Total number of deliveries per day) x 100 | Daily delivery report
■ Data collection purpose:
To measure and baseline the Project Xs and Ys
■ What to measure:
■ Sampling Plan:
All deliveries from Jan 2024 to Dec 2024

## Slide 11: Baseline Performance
Period of data collection | Total Deliveries | On-time Deliveries | OTD% | Late deliveries (defects)
Jan 2023 – Dec 2023 | 4630 | 4071 | 87.9% | 559
Process | Defects | Units | Opportu-nities per unit | Total Opportu-nities | DPU | DPO | DPMO | Sigma LT | Process Shift | Sigma ST
On-time Deliveries | 559 | 4630 | 1 | 4630 | 0.12073 | 0.12073 | 120734 | 1.17 | 1.5 | 2.67
■ Base Data:
■ Baseline DPMO & Sigma Level:

## Slide 12: Pareto Analysis (vital few causes)
83% of the late deliveries are caused by 3 causes:
▪ Schedule Variation
▪ Irregular Replenishment
▪ Misplaced Trucks

## Slide 13: Root-cause analysis (Cause & Effect)
Low OTD%
High Demand Variability
High Supply Variability
Leadtime
Resource Constraints
schedule
variation/
rush orders
Low forecast
accuracy
Seasonality
not factored
Market trends
not factored
W/H Capacity lags market demand
Ill-timed capacity investment
Inefficient
cash-to-cash management
Dispatch
Time
SOP vague
Low
efficiency
Too long
Unloading Time/
Truck turnaround
No SOP
Improperly
Trained operators
Too long
Misplaced
trucks
Location not
recorded
Incorrect Location
recorded
Driver
Count
Shortage
High driver
attrition
Manual
process
Manual
process
Irregular
Replenishment
Low forecast
accuracy
Truck/driver
shortage
W/H stock levels inaccurate
Manual stock
Update in DB
Manual
process
Promotional
offers

## Slide 14: Vital X’s summary
No. | Vital X
1 | Low forecast accuracy
2 | Market trends not factored
3 | Seasonality
4 | W/H stock levels inaccurate
5 | Ill-timed investment in W/H capacity
6 | Misplaced trucks at W/H
7 | Driver shortage
8 | W/H dispatch time is long
9 | Factory unload time is long

## Slide 15: FMEA (current process)
 | Process function | Potential failure mode | Potential effects of failure | SEV |  | Potential cause(s) of failure | OCC | Current process controls | DET | RPN | Recommended action | Responsibility and Target date
 | S&OP | Low forecast accuracy | W/H & supplier capacity inadequate vs. demand | 10 |  | S&OP process-maturity low | 6 | - | 6 | 360 | Improve S&OP maturity | Factory management; 20th Feb’24
 | S&OP | Market trends not factored | Rush orders | 8 |  | S&OP process-maturity low | 6 | - | 4 | 192 | Improve S&OP maturity | Factory management; 20th Feb’24
 | S&OP | Seasonality | Rush orders | 6 |  | S&OP process-maturity low | 4 | - | 6 | 144 | Improve S&OP maturity | Factory management; 20th Feb’24
 | Inventory recording | W/H stock levels inaccurate | Suppliers can’t know reorder point | 10 |  | Manual process | 4 | - | 6 | 240 | W/H Automation (WMS) | W/H management; 24th Jun’24
 | Truck dispatch | Late dispatch | Late Delivery | 10 |  | Inefficient process, SOP vague | 6 | - | 6 | 360 | Standardize process | W/H management; 8th Feb’24
 | Investment in capacity | Ill-timed investment | W/H capacity lags market demand | 8 |  | Cash-to-cash cycle long | 4 | - | 8 | 256 | Improve S&OP maturity | Factory management; 20th Feb’24
 | Truck location | Wrong location recorded | Truck not available for loading | 6 |  | Manual process | 4 | - | 6 | 144 | Install GPS in trucks | W/H management; 10th Feb’24
 | Driver retention | High attrition | Driver shortage | 4 |  | Low driver satisfaction | 4 | - | 6 | 96 | Driver hiring/retention best practices | W/H management; 15th Feb’24
 | Factory Unloading | Unloading too long | Late truck turnaround | 4 |  | Improper operator training, No SOP | 4 | - | 2 | 32 | Operator training, Make SOP | Factory management; 20th Feb’24

## Slide 16: Improvement action plan
No. | Cause | Improvement Action | Responsibility | Target date
1 | Low forecast accuracy | ▪Improve S&OP maturity ▪Better segmentation by channel, region & customer ▪Review forecasts at aggregate levels ▪Regularly monitor forecast accuracy | Factory management | 20th May’24
2 | Market trends not factored | ▪Improve S&OP maturity ▪Better forecast intelligence ▪Involve people with right market & product-line knowledge | Factory management | 20th May’24
3 | Seasonality | ▪Improve S&OP maturity ▪Better forecast intelligence ▪Create dashboard to monitor trends & seasonal effects | Factory management | 20th May’24
4 | W/H stock levels inaccurate | ▪Control inventory through Warehouse Management System (WMS) | W/H management | 24thJun’24
5 | Ill-timed investment in W/H capacity | ▪Improve S&OP maturity ▪Better management of cash-to-cash cycle | Factory management | 20th May’24
6 | Misplaced trucks at W/H | ▪Install GPS in trucks, integrate system with WMS | W/H management | 24th Jun’24 10th Mar’24
7 | Driver shortage | ▪Develop driver hiring & retention best practices ▪Optimize driver count | W/H management | 15th Apr’24
8 | W/H dispatch time is long | ▪Control workflow through WMS ▪Document precise SOP | W/H management | 24th Jun’24
9 | Factory unload time is long | ▪Provide operator training ▪Standardize Unload process | Factory management | 20th Apr’24

## Slide 17: Updated Process Map
Share schedule with shipping personnel/driver coordinators thru WMS (reduced lead-time & error)
Responsibility: W/H Incharge
Receive Delivery schedule from factory
▪Locate required components thru
WMS (reduced time & error)
▪Pack scheduled quantity
▪Prepare Invoice, Tax documents
▪Inform driver coordinator about dispatch
Responsibility: Shipping Personnel
Take the truck to the loading dock
Responsibility: Driver
▪ Take the truck to the Un-loading dock at customer factory
▪ Inform receiving personnel 30min before arrival
Responsibility: Driver
▪Unload the payload
▪Check Invoice, Tax documents
▪Give receipt confirmation to driver
Responsibility: Customer receiving Personnel
Check Backhaul payload with Driver coordinator
Responsibility: Driver/coordinator
Backhaul?
Yes
No
Take the empty truck back to W/H depot
Responsibility: Driver
▪Load the payload onto the truck
▪Handover Invoice, Tax documents, Gate pass to driver
Responsibility: Shipping Personnel
▪Locate suitable truck at the depot thru GPS system (reduced time & error)
▪Assign an available driver for the dispatch
▪Inform driver about dispatch details
▪Record truck request-time, dispatch-time, driver name, loading dock & destination details in WMS (reduced time & error)
Responsibility: Driver coordinator

## Slide 18: FMEA (Expected after improvement)
Process function | Potential failure mode | Potential effects of failure | Recommended action | Responsibility and Target date | Action result |  |  |  |  | 
 |  |  |  |  | Action taken |  | SEV | OCC | DET | RPN
S&OP | Low forecast accuracy | W/H & supplier capacity inadequate vs. demand | Improve S&OP maturity | Factory management; 20th Feb’24 | ▪Improved S&OP maturity ▪Better segmentation by channel, region & customer |  | 10 | 3 | 2 | 60
S&OP | Market trends not factored | Rush orders | Improve S&OP maturity | Factory management; 20th Feb’24 | ▪Improved S&OP maturity ▪Better forecast intelligence |  | 8 | 3 | 2 | 48
S&OP | Seasonality | Rush orders | Improve S&OP maturity | Factory management; 20th Feb’24 | ▪Improved S&OP maturity ▪Better forecast intelligence ▪Created dashboard to monitor trends & seasonal effects |  | 6 | 4 | 2 | 32
Inventory recording | W/H stock levels inaccurate | Suppliers can’t know reorder point | W/H Automation (WMS) | W/H management; 24th Jun’24 | Implemented WMS |  | 10 | 1 | 1 | 10
Truck dispatch | Late dispatch | Late Delivery | Standardize process | W/H management; 8th Feb’24 | ▪Implemented WMS |  | 10 | 2 | 1 | 20
Investment in capacity | Ill-timed investment | W/H capacity lags market demand | Improve S&OP maturity | Factory management; 20th Feb’24 | ▪Improved S&OP maturity ▪Better management of cash-to- cash cycle |  | 8 | 4 | 1 | 32
Truck location | Wrong location recorded | Truck not available for loading | Install GPS in trucks | W/H management; 10th Feb’24 | ▪Implemented WMS ▪Installed GPS in trucks |  | 6 | 1 | 1 | 6
Driver retention | High attrition | Driver shortage | Driver hiring/retention best practices | W/H management; 15th Feb’24 | ▪Developed driver hiring & retention best practices ▪Optimized driver count |  | 4 | 2 | 4 | 32
Factory Unloading | Unloading too long | Late truck turnaround | Operator training, Make SOP | Factory management; 20th Feb’24 | ▪Provided operator training ▪Standardized factory unload process |  | 4 | 1 | 2 | 8

## Slide 19: Expected Cost-benefit analysis
■ Project Investment $ 200k (approx.)
▪WMS
▪GPS
▪Training, SOPs, others
■ Project Savings (One year estimate) $ 50 k (approx.)
▪Cost-avoidance (sales/production losses)
▪Increased process efficiencies
▪Increased revenues
■ Net Project Savings $ 250k (approx.)

## Slide 20: Performance (Expected after improvement)
Period of data collection | Total Deliveries | On-time Deliveries | OTD% | Late deliveries (defects)
Jan 2024 – Dec 2024 | 4630 | 4071 | 87.9% | 559
■ Before Project:
RESULTS
Period of data collection | Total Deliveries | On-time Deliveries | OTD% | Late deliveries (defects)
Jul 2025 – Sep 2025 | 1520 | 1501 | 98.7% | 19
■ After Project:

## Slide 21: Performance (Expected after improvement)
Process | Defects | Units | Opportu-nities per unit | Total Opportu-nities | DPU | DPO | DPMO | Sigma LT | ProcessShift | Sigma ST
On-time Deliveries | 559 | 4630 | 1 | 4630 | 0.12073 | 0.12073 | 120734 | 1.17 | 1.5 | 2.67
RESULTS
■ Before Project:
Process | Defects | Units | Opportu-nities per unit | Total Opportu-nities | DPU | DPO | DPMO | Sigma LT | ProcessShift | Sigma ST
On-time Deliveries | 19 | 1520 | 1 | 1520 | 0.01250 | 0.012500 | 12500 | 2.24 | 1.5 | 3.74
■ After Project:

## Slide 22
Improve on-time deliveries : Conclusion
Given the achievement of the Target On-time Delivery (OTD)% and the cost-savings due to cost-avoidance (production & sales losses) and increased operational efficiencies, the Project was declared to be successful by the Customer and the Stakeholders.
It was also clear that every effort must be made to sustain the improvements.